## Risk Identification
Category | Risk | Probability | Impact | Response
Technical | Third-party mapping/navigation API failure | Medium | High | Monitor API performance; implement error handling and fallback procedures.
Technical | Payment processing integration failure | Medium | High | Test payment integration early; maintain sandbox testing and failure handling.
Technical | Inaccurate real-time parking availability data | Medium | High | Validate occupancy data; implement data validation and discrepancy monitoring.
Technical | Security or user data vulnerability | Medium | High | Conduct security testing; use secure authentication and encryption practices.
Schedule | Third-party API integration takes longer than planned | Medium | Medium | Begin integrations early; maintain schedule buffer for integration work.
Schedule | Testing requires more time than scheduled | Medium | High | Begin testing incrementally; prioritize critical functionality and maintain testing buffer.
Schedule | Requirement changes cause development delays | Medium | Medium | Manage changes through the product backlog and prioritize changes by impact.
Schedule | Dependencies between development teams cause delays | Medium | High | Coordinate dependencies during sprint planning and regular team meetings.
Financial | Third-party API/service costs exceed estimates | Medium | Medium | Monitor service usage and evaluate alternative providers when appropriate.
Financial | Cloud infrastructure costs exceed estimates | Low | Medium | Monitor resource utilization and adjust infrastructure as necessary.
Financial | Rework increases development costs | Medium | Medium | Review requirements and designs early; use incremental testing to identify issues sooner.
Financial | Security/compliance requirements create additional costs | Low | Medium | Identify compliance requirements early and account for them during planning.
People | Loss or unavailability of a key team member | Low | High | Cross-train team members and maintain project documentation.
People | Poor communication between development teams | Medium | High | Conduct regular team meetings and document cross-team dependencies.
People | Team lacks expertise with a required technology | Medium | Medium | Provide training and assign experienced team members to specialized work.
People | Stakeholder disagreements delay project decisions | Medium | Medium | Document requirements and establish a clear process for stakeholder decisions.

## Risk Register
ID | Description | Probability | Impact | Owner | Response Strategy | Status/Notes
R-01 | Third-party mapping/navigation API failure | Medium | High | William Cooke | Mitigate | Open - Monitor API performance; implement error handling and fallback procedures.
R-02 | Payment processing integration failure | Medium | High | William Cooke | Mitigate | Open - Test payment integration early; maintain sandbox testing and failure handling.
R-03 | Inaccurate real-time parking availability data | Medium | High | Charles Byrne | Mitigate | Open - Validate occupancy data; implement data validation and discrepancy monitoring.
R-04 | Security or user data vulnerability | Medium | High | Chalres Byrne | Mitigate | Open - Conduct security testing; use secure authentication and encryption practices.
R-05 | Third-party API integration takes longer than planned | Medium | Medium | William Cooke | Mitigate | Open - Begin integrations early; maintain schedule buffer for integration work.
R-06 | Testing requires more time than scheduled | Medium | High | Ayden Moss | Mitigate | Open - Begin testing incrementally; prioritize critical functionality and maintain testing buffer.
R-07 | Requirement changes cause development delays | Medium | Medium | Alex Rivera | Mitigate | Open - Manage changes through the product backlog and prioritize changes by impact.
R-08 | Dependencies between development teams cause delays | Medium | High | Alex Rivera | Mitigate | Open - Coordinate dependencies during sprint planning and regular team meetings.
R-09 | Third-party API/service costs exceed estimates | Medium | Medium | William Cooke | Mitigate | Open - Monitor service usage and evaluate alternative providers when appropriate.
R-10 | Cloud infrastructure costs exceed estimates | Low | Medium | Paige Hoffman | Mitigate | Open - Monitor resource utilization and adjust infrastructure as necessary.
R-11 | Rework increases development costs | Medium | Medium | Alex Rivera | Mitigate | Open - Review requirements and designs early; use incremental testing to identify issues sooner.
R-12 | Security/compliance requirements create additional costs | Low | Medium | Alex Rivera | Mitigate | Open - Identify compliance requirements early and account for them during planning.
R-13 | Loss or unavailability of a key team member | Low | High | Alex Rivera | Mitigate | Open - Cross-train team members and maintain project documentation.
R-14 | Poor communication between development teams | Medium | High | Alex Rivera | Mitigate | Open - Conduct regular team meetings and document cross-team dependencies.
R-15 | Team lacks expertise with a required technology | Medium | Medium | Charles Byrne | Mitigate | Open - Provide training and assign experienced team members to specialized work.
R-16 | Stakeholder disagreements delay project decisions | Medium | Medium | Alex Rivera | Mitigate | Open - Document requirements and establish a clear process for stakeholder decisions.
The Risk Register has been updated to assign ownership to specific project team members based on the roles established in the Resource Plan. Technical and integration risks are assigned to the appropriate specialists, while broader scheduling, staffing, and stakeholder risks remain under the Project Manager. These assignments improve accountability and establish clear responsibility for monitoring and responding to risks throughout the project.

## Communication Plan
Meeting/Report | Cadence | Method | Participants | Purpose/Notes
Team Stand-Up | Twice weekly | Teams / Virtual Meeting | All eight project team members | Share progress, identify blockers, and coordinate current development tasks.
Sprint Planning | Beginning of each sprint | Teams / Virtual Meeting | Alex Rivera, Charles Byrne, and the development team | Select sprint backlog items, establish sprint goals, and coordinate team responsibilities.
Weekly project Status Report | Weekly | Email / Written Report | Alex Rivera --> Project Stakeholders | Summarize project progress, schedule status, completed work, upcoming activities, and major risks.
Sprint Review | End of each sprint | Teams / Demonstration | Project team and stakeholders | Demonstrate completed functionality, collect stakeholder feedback, and identify needed changes.
Risk Review | Weekly | Teams / Risk Register | Alex Rivera and relevant risk owners | Review open risks, evaluate changes in probability or impact, and track mitigation actions.
Ad-Hoc Risk Escalation | As needed | Teams / Email | Alex Rivera, risk owner, affected team members | Escalate critical risks, issues, or blockers requiring immediate attention or decisions.
Project Closure Meeting | Once at project completion | Teams / Virtual Meeting | All eight team members and key stakeholders | Review final deliverables, obtain approval, document lessons learned, and formally close the project.
The Communication Plan has been refined to align with the finalized project staffing structure and Risk Register. Meeting participants and reporting responsibilities now reflect the established project roles, with risk owners involved in relevant reviews and escalations. The existing meeting schedule and communication methods remain unchanged, as they continue to support the project's planned development activities.