## Roles & Resources
Role | Name | Skill Level | Allocation %
Project Manager | Alex Rivera | Senior | 50%
Technical Lead / Backend Developer | Charles Byrne | Senior | 75%
Frontend / Web Developer | Taylor Pearce | Mid-level | 75%
Mobile Developer | Brittany Nguyen | Mid-level | 75%
UI/UX Designer | Lexi Harper | Mid-level | 50%
Integration Developer | William Cooke | Senior | 50%
QA Tester | Ayden Moss | Mid-level | 50%
DevOps / Database Engineer | Paige Hoffman | Senior | 40%
The project team consists of eight fictional members assigned based on the technical and management requirements of the Smart Parking Platform. Each member has an assumed skill level and resource allocation reflecting their responsibilities. Development roles receive higher allocations during implementation, while design, testing, and infrastructure roles are assigned according to their expected workloads. This structure supports the project's specialized functional areas while allowing resources to be shared.

## Resource Plan
Role | Name | FTE % | Active Months | Estimated Hours | Hourly Rate | Cost
Project Manager | Alex Rivera | 50% | 4 | 320 | 65 | 20800
Technical Lead / Backend Developer | Charles Byrne | 75% | 3 | 360 | 70 | 25200
Frontend / Web Developer | Taylor Pearce | 75% | 2 | 240 | 50 | 12000
Mobile Developer | Brittany Nguyen | 75% | 2 | 240 | 55 | 13200
UI/UX Designer | Lexi Harper | 50% | 2 | 160 | 45 | 7200
Integration Developer | William Cooke | 50% | 2 | 160 | 65 | 10400
QA Tester | Ayden Moss | 50% | 3 | 240 | 45 | 10800
DevOps / Database Engineer | Paige Hoffman | 40% | 3 | 192 | 65 | 12480
Total |  |  |  | 1912 |  | 112080
The resource plan estimates labor costs using a bottom-up approach based on each team member's allocation, active months, and assumed hourly rate. Resource commitments vary according to project responsibilities, with development personnel concentrated during implementation and specialized roles supporting design, integration, testing, and deployment. The estimated total labor requirement is 1,912 hours, resulting in a projected labor cost of $112,080. These estimates provide the foundation for the overall project cost plan and may be adjusted as scheduling and resource requirements are refined.

## Resource & Cost Plan
Item | Category | Qty / Months | Unit Cost | Duration | Total
Labor (from Resource Plan) | Personnel | 1,1912 hours | Varies | 4 months | 112080
Cloud Hosting & Database | Infrastructure | 4 months | $300/mo | 4 months | 1200
Mapping & Navigation APIs | Services | 3 months | $200/mo | 3 months | 600
Payment Processing / Testing | Services | 2 months | $150/mo | 2 months | 300
Design Tools | Software | 2 months | $75/mo | 2 months | 150
Testing & Development Tools | Software | 3 months | $100/mo | 3 months | 300
Project Management Tools | Software | 4 months | $50/mo | 4 months | 200
Deployment & Launch | Operations | One-time | 1000 | — | 1000
Subtotal |  |  |  |  | 115830
Contingency (10%) | Reserve | 10% | — | — | 11583
Grand Total |  |  |  |  | 127413
The Smart Parking Platform cost plan uses a bottom-up estimation approach, combining projected labor expenses with infrastructure, third-party services, software tools, and deployment costs. Labor represents the largest portion of the budget at $112,080, based on the previously established resource plan. A 10% contingency reserve is included to account for unforeseen expenses and project risks. The total estimated project budget is $127,413. Although the project assumes an unrestricted theoretical budget, cost planning remains important for resource efficiency, financial visibility, and project management.

## Monthly Budgeted Cash Flow
Month | Planned Labor | Planned Non-Labor | Contingency Reserve | Total Budget | Cumulative Budget
September | 22000 | 450 | 0 | 22450 | 22450
October | 40000 | 1050 | 0 | 41050 | 63500
November | 36000 | 1150 | 0 | 37150 | 100650
December | 14080 | 1100 | 0 | 15180 | 115830
Unallocated Reserve | 0 | 0 | 11583 | 11583 | 127413
Total | 112080 | 3750 | 11583 | 127413 | 127413
The monthly cash flow forecast distributes planned project expenditures across the September–December 2026 development schedule. Spending is expected to increase during October and November as development, integration, and testing activities overlap. December reflects reduced staffing requirements as the project transitions toward deployment and closure. A separate contingency reserve is maintained for unforeseen costs. The forecast will be revised as resource assignments and project scheduling become more detailed.

## RACI Matrix
Task / Deliverable | PM | TL | WEB | MOB | UX | INT | QA | OPS | Role Abbreviation | Team Member
Requirements Gathering | A/R | C | I | I | R | C | C | I | PM | Alex Rivera
System Architecture | C | A/R | C | C | I | R | C | R | TL | Charles Byrne
UI/UX Design | I | C | R | R | A/R | INT | C | I | WEB | Taylor Pearce
User Authentication Development | I | A/R | R | R | C | C | C | C | MOB | Brittany Nguyen
Parking & Garage Development | I | A/R | R | R | C | R | C | R | UX | Lexi Harper
Reservation & Navigation Development | I | A | R | R | C | R | C | C | INT | William Cooke
Payment & Billing Development | I | A | R | R | C | R | C | C | QA | Ayden Moss
Operator Dashboard & Reporting | I | A | R | C | R | C | C | R | OPS | Paige Hoffman
Integration Testing | I | C | R | R | I | R | A/R | C
System & Acceptance Testing | I | C | C | C | C | C | A/R | I
Production Deployment | C | R | C | C | I | R | C | A/R
Project Closure & Approval | A/R | C | I | I | I | C | C | R
The RACI matrix establishes clear responsibilities and accountability across the Smart Parking Platform's major project activities. Each deliverable has one accountable team member, while responsibility for execution is distributed according to individual technical expertise. Development activities involve collaboration between backend, web, mobile, and integration personnel, while quality assurance and deployment have designated ownership. This structure supports effective coordination, reduces confusion over responsibilities, and aligns team assignments with the project's resource and communication plans.