## WBS
CODE | TASK | Parent Task
1 | Project Initiation | -
1.1 | Requirements Gathering | 1
1.1.1 | Stakeholder Requirements | 1.1
1.1.2 | Competitive Analysis | 1.1
1.2 | Vision and Scope | 1
1.2.1 | Project Vision | 1.2
1.2.2 | Project Scope | 1.2
1.3 | Software Requirements Specification | 1
1.3.1 | Functional Requirements & Use Cases | 1.3
1.3.2 | Nonfunctional Requirements | 1.3
2 | System Design | -
2.1 | System Architecture | 2
2.1.1 | Web & Mobile Architecture | 2.1
2.1.2 | Backend & API Architecture | 2.1
2.2 | User Interface Design | 2
2.2.1 | Driver Interface Design | 2.2
2.2.2 | Operator Dashboard Design | 2.2
2.3 | Database Design | 2
2.3.1 | User & Vehicle Data | 2.3
2.3.2 | Parking, Reservation, & Transaction Data | 2.3
3 | Development | -
3.1 | User & Authentication Development | 3
3.1.1 | Registration & Login | 3.1
3.1.2 | Profile & Vehicle Management | 3.1
3.2 | Parking & Garage Development | 3
3.2.1 | Real-Time Parking Availability | 3.2
3.2.2 | Parking Search & Interactive Map | 3.2
3.2.3 | Garage Management | 3.2
3.3 | Reservation & Navigation Development | 3
3.3.1 | Parking Reservations | 3.3
3.3.2 | Navigation & Notifications | 3.3
3.4 | Payment & Billing Development | 3
3.4.1 | Digital Payment Processing | 3.4
3.4.2 | Receipts & Refunds | 3.4
3.5 | Operator & Reporting Development | 3
3.5.1 | Occupancy Monitoring | 3.5
3.5.2 | Reporting & Analytics | 3.5
4 | Testing | -
4.1 | Functional Testing | 4
4.1.1 | Web & Mobile Application Testing | 4.1
4.1.2 | Operator Dashboard Testing | 4.1
4.2 | Integration Testing | 4
4.2.1 | Mapping & Navigation Integration Testing | 4.2
4.2.2 | Payment Integration Testing | 4.2
4.3 | Security & Performance Testing | 4
4.3.1 | Security & Privacy Testing | 4.3
4.3.2 | Performance & Load Testing | 4.3
4.4 | User Acceptance Testing | 4
4.4.1 | Driver Acceptance testing | 4.4
4.4.2 | Parking Operator Acceptance Testing | 4.4
5 | Deployment | -
5.1 | Production Environment Setup | 5
5.1.1 | Server & Database Configuration | 5.1
5.1.2 | Production System Configuration | 5.1
5.2 | Production Deployment | 5
5.2.1 | Web Application Deployment | 5.2
5.2.2 | Mobile Application Deployment | 5.2
5.3 | Deployment Documentation | 5
5.3.1 | User Documentation | 5.3
5.3.2 | Operator Documentation | 5.3
6 | Project Closure | -
6.1 | Stakeholder Handover | 6
6.1.1 | Operator Training | 6.1
6.1.2 | System Administrator Handover | 6.1
6.2 | Final Project Review | 6
6.2.1 | Final Stakeholder Approval | 6.2
6.2.2 | Project Sign-Off | 6.2

## Gantt
Task | Start | Finish | Duration (days) | Start Offset
Project Initiation & Requirements | 2026-09-01 | 2026-09-18 | 18 | 0
System Architecture & Design | 2026-09-14 | 2026-09-30 | 17 | 13
UI/UX Design | 2026-09-21 | 2026-10-02 | 12 | 20
User & Authentication Development | 2026-10-01 | 2026-10-16 | 16 | 30
Parking & Garage Development | 2026-10-01 | 2026-10-23 | 23 | 30
Reservattion & Navigation Development | 2026-10-12 | 2026-10-30 | 19 | 41
Payment & Billing Development | 2026-10-12 | 2026-10-30 | 19 | 41
Operator Dashboard & Reporting | 2026-10-19 | 2026-11-06 | 19 | 48
Integration Testing | 2026-11-02 | 2026-11-13 | 12 | 62
System & Acceptance Testing | 2026-11-09 | 2026-11-25 | 17 | 69
Deployment | 2026-11-30 | 2026-12-04 | 5 | 90
Project Closure | 2026-12-07 | 2026-12-11 | 5 | 97
*Project Timeline Gantt Chart (Days from September 1, 2026)